## Slide 1: Lone worker project summary
We’ve changed how we work
HSE recommendations in 2016
Changes to sentencing guidelines
Organisational risk
Existing lone worker system is flaky and doesn’t meet BS8484
We need a technical and OD project to deliver lone worker safety devices and training

## Slide 2: Choosing the methodology
Prince - Why?
Prince – which parts of the methodology add value?
  Business case asking for spending commitment
  PID with a clear set of objectives together with a clearly defined approach to delivery and handover to support
  Highlights – the project needs to be highly visible and have management buy-in down to third level
  Project plan/timescales

## Slide 3: Estimating the project
Supplier discussions to shape cost model – devices and training
Role categories developed with OD and H&S to estimate scale – constantly refined
High figures used rather than a range approach
Horizon scanning
Business case to SLT to present the estimates and agree budget

## Slide 4: Planning the project
Project owner to sign off PID and Business Case
SLT to agree business case
MS Project for gant chart and responsibilities.
PID - > Business Case -> Training package and wrap -> roll-out plan -> BaU
MS Teams for all project docs
Use procurement lag to engage third tier managers
GDPR PIA completed
Met with unions
Long-term sustainability and revenue commitment for BAU
Risks and issues
Monthly highlight reports for SLT

## Slide 5: Resources
Project team - me, OD and H&S leads. Roles and responsibilities clearly defined and understood
Compelling business case puts costs against risks
Buy-in from operational managers by making a strong case face to face - everyone understands the objective
Internal comms

## Slide 6: Summary Approval, authority and visibility throughout the lifecycle